## Sheet1
No | Issue | Description | status | Android | iOS | Confirmed
1 | Change username to be username and mobile in login and forget password. | Just name of label text |  |  | Done
2 | Handle Inactive user when he want to login | When try to login and recive error code "InActiveUser:8", show user the error message then redirect user to virification code page and requiest to api "api/Account/ResendCode" without data just pass token come from login
3 | Add continue as gest in login page | in login page add button "Continue as a gest" which redirect user to car list page without login
4 | Add logo in select langauge | Replace Language logo with new E-Rent logo
5 | When book a car then register go back to this car | After click on car item then show register message and redirect user to login page, now if he login or register system should redirect him back to this car to book in directly insted of search again for it
6 | Implement resend verfication code | after user go to virification code system wait 60 second untile active resend code again, also when user click on resend the code call api "api/Account/ResendCode"
7 | Fix space after every filed in register | if user click on input to write his data (egx: email) and while inserting email; keyboard suggest to inter saved emails append with space. after check this email, the check is invalid because the space after email. so what I want is remove the space after email before check it if is valid email or not.
8 | Change logo and colors | As I will send to you
9 | Remove check mobile number start with 05 | Remove any check on mobile number, and remove "+966" so allow user to insert any number and with any digits, because we register with sms provider who will check on them. do not allow user to insert nothing; this is required field
10 | Before verfication show popup to validate mobile number. | After signup and before go to verfication code page show user validate message to verify mobile number with tow option, contine or edit
11 | Add full name to register | add new field in signup wich is "FullName" and make it required
12 | Change address to subject in arabic | in contact us please change translate of subject from "العنوان" to "الموضوع"