## Sheet1
Number | Issue | Description | suggestion | priorety
1 | Language in first screen | please select language in main screen | - | Low
2 | username translate | must be user name not name | اسم المستخدم وليس الاسم لأنه يفهم هنا انه الاسم الكامل | Low
3 | id translate | must be id or iqama | الهوية / الإقامة | Low
4 | id input | should be like phone number | تسمح بأرقام فقط | Low
5 | day coast main list | show day cost in every car itemin the list | you can replace it with color, but it should shown | High
6 | disable delivery to location | - | in book this car page if user click on delivery to location show him message "it wil be soon" | Low
7 | change way to get birthday | choose year is not easy and birthday always before this year | maybe we should replace it with dropdown list | High
8 | large image in register | if you choose large image for id and licence request return 500(internal server error) and request doesn’t go to api | we should limit image size or increse size of request or send image with different request | critical
9 | close booking in request page | remove "x" icone from close and user must be choose accept or reject the request | - | High
10 | close booking in request page | remove close booking button from done request | - | Low
11 | add year in search critiria | must be search with it | - | High
12 | model and type of car in search | if we choose type and want to determine model then all car models shown | - | critical
13 | search not working | if we fillter on anything there is no result found | - | critical
14 | car list pages | if we have large number of cars we should show them as paging | we need to discuss about it and find best solution | Low
15 | car icon | car icon is cutted | increase width of car icon. | Low
16 | history in profile | doesn’t show anything | now done request must be shown here but in request page there are done and pending request !! | Low
17 | E-rent icon in profile | there are tow logo in profile page | remove one of them | Low